## Summary
Hydris Field Glasses: Production Readiness Plan
Inventory of what is built, corrections, enhancements, and a 30-day plan with 2 to 3 work sessions per day.
Plan start | 2026-10-27 | Phases
Plan end | 2026-11-25 | Phase 1: Foundations and critical fixes | Days 1-7 | CI, security fixes, Android release signing, bridge hardening
Days | 30 | Phase 2: Backend hardening and data | Days 8-14 | Jobs, email, object storage, observability, contracts, staging
Work sessions |  | Phase 3: Mobile and frontend production quality | Days 15-21 | Android MFA, inspections + offline, tests, design tokens, Play internal
Sessions done |  | Phase 4: Hardware validation, AI quality, pilot readiness | Days 22-28 | Ray-Ban tests, OCR and voice benchmarks, load, DR, security review
Progress |  | Phase 5: Release | Days 29-30 | Release candidate, production, go/no-go, hypercare
Backend components
Frontend components |  | Session guideline
Corrections |  | S1 (2.5 h, deep work): the main feature or fix of the day.
Corrections open |  | S2 (2.5 h): second item, tests, or finishing S1.
Enhancements |  | S3 (1.5 h, optional): review, docs, regression, planning.
P0 enhancements |  | Every session: branch, small PR, tests added, CI green, update the Status column.
Definition of done is in each row; do not mark Done without it.

## Backend
Area | Component | What it does | Status | Location
API modules | Auth (17 routes) | Password login, sessions with rotating refresh, MFA (TOTP), password reset, invitations, demo login with named guest accounts | Built | apps/api/src/modules/auth.ts
API modules | Organization (13) | Org settings, members, roles, invitations, audit log, platform admin | Built | modules/org.ts
API modules | Plant (28) | Sites, process areas, assets, sensors, plant map, documents/SOPs, attachments | Built | modules/plant.ts
API modules | Telemetry (6) | HTTPS ingest with API keys, idempotent readings, history, corrections, freshness | Built | modules/telemetry.ts
API modules | Alarms (9) | Rule evaluation, lifecycle (acknowledge, investigate, resolve with note, close), assignment | Built | modules/alarms.ts
API modules | Inspections (15) | Templates, rounds, step responses with offline op replay, submit, review | Built | modules/inspections.ts
API modules | Maintenance (7) | Work requests, assignment, execution, activity log | Built | modules/maintenance.ts
API modules | Devices and pairing (16) | RFC 8628-style pairing (300 s code), device tokens, suspend/revoke/reassign, glasses logout | Built | modules/devices.ts
API modules | UI profiles (13) | What each glasses screen shows; draft, publish, rollback, live push | Built | modules/ui-profiles.ts
API modules | Audit documents (12) | Scan upload, OCR structuring, cross-check, plausibility, vision enhance, field review, second-person approval, searchable PDF | Built | modules/audit-docs.ts, core/audit-pdf.ts, core/vision-extract.ts
API modules | Voice assistant (1) | Grounded answers from account data: readings, alarms, my work, assets, SOPs; Claude tool use or rules engine | Built | modules/voice-assistant.ts
API modules | Insights (4) | Overview dashboard, reports, search, assist | Built | modules/insights.ts
API modules | Realtime (1) | Server-sent events (18 domain event types), memory or db mode | Built | modules/realtime.ts, app/api/events/stream
API modules | Simulation (3) + Public (1) | Demo scenarios and synthetic telemetry; contact / demo request | Built | modules/simulation.ts, public.ts
Platform | Health and cron | /api/health, /api/cron (daily on Vercel) | Partial | vercel.json, jobs.ts
Platform | Tenancy and RLS | Postgres row-level security; withTenant/withSystem; 36 of 42 tables with RLS | Built | core/*, drizzle/*.sql
Platform | Demo mode | In-memory per instance, shared state via Postgres kv / Vercel cache, stateless demo device tokens | Built | core/demo-shared.ts, core/demo-guests.ts
Data | Database schema | 42 tables, 548 columns, 23 enums, 9 migrations, 71 indexes | Built | apps/api/src/db/schema.ts
Domain | Domain package | Audit doc structuring, plausibility, voice wake/measurand detection, roles (38 permissions, 6 roles), UI profile rules | Built | packages/domain/src
Quality | Automated tests | 67 passing: 26 domain + 41 API; 4 Playwright journeys | Built | packages/domain/test, apps/api/test, tests/e2e
Deployment | Vercel + Postgres | Next.js with API in-process at hydrisview.vercel.app; Neon-ready | Built | vercel.json, apps/web/src/app/api/[...path]
Email | Mail delivery | Messages only written to mail_outbox; nothing is sent | Partial | mail_outbox
Storage | File storage | Audit page images stored base64 in Postgres | Partial | audit_document_pages
CI/CD | Pipeline | No GitHub Actions; deploys straight from main | Planned | .github (missing)

## Frontend
Area | Component | What it does | Status | Location
Website | Public site | Home, product, technology, operations, demo, contact, privacy; demo request | Built | apps/web/src/app/(site)
Website | Login and demo | Sign in, MFA, forgot/reset password, one-click named demo account | Built | app/login
Console | Overview | KPIs, process snapshot, alarm frequency, connectivity | Built | app/console/page.tsx
Console | Alarms | List, severity filters, lifecycle actions, notes | Built | console/alarms
Console | Telemetry | Sensor cards and table, history charts, freshness | Built | console/telemetry
Console | Plant: sites, assets, map | Hierarchy management and plant map with routes | Built | console/sites, assets, map
Console | Inspections and maintenance | Templates, pipeline, review, work orders | Built | console/inspections, maintenance
Console | Documents / SOPs | Approved procedures, versions, search | Built | console/documents
Console | Field glasses and profiles | Pairing approval, device states, UI profile editor | Built | console/devices, glasses-profiles
Console | Audit documents | Review queue, field-by-field verify, approve, PDF download | Built | console/audit-docs
Console | Reports, operators, audit log, settings, platform | Admin and reporting screens | Built | console/reports, operators, audit, settings, platform
Glasses web app | HUD and phone modes | 12 screens, back navigation, menu, logout/unpair, offline inspection queue, voice, audit scan with guided capture | Built | apps/web/src/glasses
Glasses web app | Simulator and pairing page | Browser glasses simulator with scenarios; /pair approval | Built | app/simulator, app/pair
Android | Hydris Field app (Kotlin/Compose) | Login + demo, Home dashboard, Work (alarms/inspections/tasks/sensors), Scan (glasses, phone, import), Hydris assistant, Glasses tab, SSE notifications | Built | apps/android
Android | Ray-Ban Meta via DAT | Registration, camera stream and photo, capture button, glasses speech | Partial | glasses/GlassesManager.kt (not run on real hardware)
Android | Glasses bridge (WebView) | Companion app hosting the glasses web app with the DAT bridge | Partial | apps/glasses-bridge-android
Android | Inspections step entry, offline outbox, MFA | Not in the native app yet | Planned | apps/android
Docs | Product documentation | 13-document suite, 99-page Product Book, 60-page PRD, Word + PDF generator | Built | docs/product

## Corrections
ID | Area | Issue | Impact | Severity | Fix | Status
C01 | Android / repo | Root .gitignore "data" excluded the Android data/ source package | Fresh clone could not compile | Critical | Negation rule added; files committed | Done
C02 | Android | Resolve sent no note; API returns note_required | Resolve always failed | High | Note field added; Resolve disabled until filled | Done (verify on device)
C03 | Security / API | GET /api/attachments/:id checks org only, not site scope | Members can download files of sites they cannot see | High | Check site scope of the owning record before streaming | Open
C04 | Security / DB | App connects as owner role, which bypasses RLS | RLS is not enforced if a query forgets the tenant filter | High | Separate migration owner and runtime role (NOBYPASSRLS) | Open
C05 | Android | Release build signed with the debug key | Cannot ship to Play; insecure | High | Release keystore via env/CI secrets; Play App Signing | Open
C06 | Glasses bridge | WebView grants every permission and does not restrict navigation | Other pages get the native bridge and camera/mic | High | Allow-list origin, restrict navigation, scoped permission grant | Open
C07 | Repo | Debug APK committed (apps/glasses-bridge-android/hydris-glasses-debug.apk) | Binary in repo, stale build | Medium | Remove from git history going forward; publish via releases | Open
C08 | Security / web | Helmet CSP disabled | No XSS defence-in-depth | Medium | Enable CSP with nonces for Next.js | Open
C09 | Web | Permissions-Policy microphone=() blocks browser speech on /glasses | Voice fails on display glasses in browser | Medium | Allow microphone=(self) on /glasses | Open
C10 | Security / API | trustProxy: true lets clients spoof X-Forwarded-For | Rate limits bypassable on container deploys | Medium | Trust only the platform proxy hop count | Open
C11 | API | Rate limiter stores counts per serverless instance | Limits ineffective on Vercel | Medium | Shared store (Upstash Redis or Postgres) | Open
C12 | Glasses web | Device refresh token and data cache in localStorage | Token theft via XSS | Medium | Move to httpOnly cookie or short-lived token + IndexedDB with encryption | Open
C13 | Jobs | Vercel cron runs daily (0 3 * * *) | Stale-data alarms and pairing expiry only daily | High | Per-minute scheduler (Vercel Pro cron or external) + idempotent jobs | Open
C14 | Ops | /api/health does not check the database | False healthy status | Low | Add DB ping and version info | Open
C15 | Build | Node version mismatch: engines 22.x vs Dockerfiles 24 | Inconsistent runtime | Low | Align on Node 22 LTS everywhere | Open
C16 | Email | Email not sent; mail_outbox keeps live reset/invite links with no purge | Users cannot reset passwords; sensitive links retained | High | Wire a provider (Resend/SES), mark sent_at, purge after 7 days | Open
C17 | Storage | Audit page images stored base64 in Postgres | DB bloat, slow queries, cost | Medium | Move to object storage (Vercel Blob/S3) with signed URLs | Open
C18 | Data | No retention or purge jobs | Unbounded growth, DPDP exposure | Medium | Retention schedule + purge jobs per table | Open
C19 | Design | HUD text #141714 on Signal Blue is 3.08:1; Android severity chips 3.2 to 3.8:1 | Fails WCAG AA | Medium | White text on blue; darken chip fills | Open
C20 | Design | High-severity colour differs: #FF9F1C console, #FF5A1F site, #F26414 Android/HUD | Inconsistent meaning | Low | Single token #F26414 shared from one source | Open
C21 | Android | Action buttons ignore the API allowedActions | Users see actions they cannot perform | Medium | Render buttons from allowedActions | Open
C22 | Android | Home "All sensors" opens Work on the Alarms tab | Wrong navigation | Low | Navigate to the Sensors tab | Open
C23 | Android / DAT | stopPreview() stops forwarding frames but not the DAT camera stream | Battery drain on glasses | Medium | Stop the stream / close camera on preview stop | Open
C24 | Android | Registering glasses always assigns the first visible site | Wrong site assignment | Medium | Site picker during registration | Open
C25 | Android | Native app and bridge derive different hardware IDs | One pair of glasses becomes two devices | Medium | Single shared hardware-ID derivation | Open
C26 | Android | Device-token refresh has no mutex | Refresh races, forced re-pair | Medium | Mutex like the user-session refresh | Open
C27 | Android build | settings.gradle.kts lacks the GitHub Packages repo for DAT; DataStore unused | Clean builds can fail | Medium | Declare repo with read:packages token; remove unused dep | Open
C28 | Android | No MFA flow; MFA users told to use the web | Blocks secure accounts on mobile | High | Implement TOTP step in LoginScreen | Open
C29 | Data | Missing FKs on device/actor ids; no GIN index for document search; unused processing status | Integrity and search performance | Low | Migration adding FKs, GIN index; drop or use status | Open
C30 | Roles | Viewer (auditor persona) lacks audit.read | Auditors cannot open the audit log | Low | Product decision, then update roles.ts | Decide
C31 | Deploy | Migrations run on cold start (vercel-build unused) | Slow cold starts, risky concurrent migrations | Medium | Run migrations in CI/deploy step | Open
C32 | Contracts | packages/contracts is empty; Android mirrors JSON by hand | Contract drift | Medium | Generate OpenAPI + Kotlin models | Open
C33 | Docs | PRD says Resolve sends no note; pairing TTL 10 min in vercel.md vs 300 s; per-minute cron in docs | Docs drift | Low | Update PRD.md, docs/operations/vercel.md | Open
C34 | Code comment | docdetect.ts says 1240x1754 at 150 dpi; code uses 1654x2339 at 200 dpi | Misleading | Low | Fix comment | Open

## Enhancements
ID | Area | Enhancement | Value | Effort (days) | Priority | Phase
E01 | CI/CD | GitHub Actions: typecheck, unit + API tests, Playwright, web build, Android assemble, migration check | Every change verified before deploy | 2 | P0 | Phase 1
E02 | Observability | Sentry (web, API, Android), structured logs, uptime checks, alerting | Find and fix production issues fast | 2 | P0 | Phase 2
E03 | Email | Transactional email provider for invites, resets, alarm escalations | Self-service accounts | 1 | P0 | Phase 2
E04 | Storage | Object storage for audit images and attachments with signed URLs | Scale and cost | 2 | P0 | Phase 2
E05 | Jobs | Reliable per-minute background jobs (stale data, escalation, pairing expiry, purge) | Alarms on time | 1 | P0 | Phase 2
E06 | Android | Inspections step entry on the phone + offline outbox (Room) with replay | Field rounds without signal | 3 | P0 | Phase 3
E07 | Android | MFA (TOTP) sign-in | Secure accounts on mobile | 1 | P0 | Phase 3
E08 | Android | Unit and UI tests (DocDetect, OCR pairing, repository, screens) | Regression safety | 2 | P0 | Phase 3
E09 | Android | Release signing, R8, Play internal testing track | Installable by pilot users | 1 | P0 | Phase 3
E10 | Glasses | Ray-Ban Meta hardware validation GLS-T01 to T15 (camera, capture button, speech, registration) | Proves the glasses path | 3 | P0 | Phase 4
E11 | AI / OCR | OCR benchmark set (120 pages) and accuracy dashboard | Measured accuracy for auditors | 2 | P1 | Phase 4
E12 | AI / Voice | Voice utterance test set, wake-word tuning, latency targets | Reliable hands-free use | 1 | P1 | Phase 4
E13 | Contracts | OpenAPI generated from zod schemas; typed web client and Kotlin models | No contract drift | 2 | P1 | Phase 2
E14 | Performance | Load tests (k6) for ingest, SSE, dashboard; DB indexes | Known capacity | 1 | P1 | Phase 4
E15 | Security | Dependency and secret scanning, CSP, security headers, pen-test checklist | Customer security review ready | 2 | P0 | Phase 1
E16 | Glasses | Photo steps captured with the glasses camera (FR-045) | Evidence without the phone | 1 | P1 | Phase 3
E17 | Design | Single design-token source (web, HUD, Android) and contrast fixes | Consistent, accessible UI | 1 | P1 | Phase 3
E18 | Backup / DR | Point-in-time restore drill, backup runbook, RPO/RTO targets | Recoverability | 1 | P1 | Phase 4
E19 | Compliance | Audit trail export, e-signature on approvals (Planned design) | Regulatory record integrity | 2 | P2 | After month
E20 | Localisation | Hindi and Tamil for glasses and Android (strings catalogue first) | Operator adoption | 2 | P2 | After month
E21 | Integrations | Edge gateway with MQTT / OPC UA ingestion | Real plant data without custom work | 10 | P2 | After month
E22 | Reports | CPCB/SPCB and OCEMS compliance reports | Regulatory value | 5 | P2 | After month
E23 | Android | Certificate pinning, Play Integrity, root detection | Mobile hardening | 1 | P1 | Phase 3
E24 | Accessibility | Haptics, chart descriptions, larger outdoor text | Gloved / outdoor use | 1 | P2 | Phase 3

## 30-Day Plan
Day | Date | Weekday | Phase | Session | Task | Area | Refs | Guideline (steps) | Definition of done | Status | Owner | Notes
1 | 2026-10-27 | Tue | Phase 1: Foundations and critical fixes | S1 09:30-12:00 | Baseline and branch strategy | Repo | C07, C15 | Create dev branch + PR rule; remove committed APK; align Node 22; record current test pass | main protected; npm test green; APK out of repo | Not started
1 | 2026-10-27 | Tue | Phase 1: Foundations and critical fixes | S2 14:00-16:30 | CI pipeline v1 | CI/CD | E01 | GitHub Actions: install, typecheck, domain + API tests, web build; cache npm | CI runs on every PR and passes | Not started
1 | 2026-10-27 | Tue | Phase 1: Foundations and critical fixes | S3 17:00-18:30 | Review and plan | All | - | Triage this sheet; assign owners; set up issue board | Board with every C and E item | Not started
2 | 2026-10-28 | Wed | Phase 1: Foundations and critical fixes | S1 09:30-12:00 | Attachment site-scope check | API | C03 | Look up owning record, requireSite before streaming; add API test | Test proves cross-site download is 404 | Not started
2 | 2026-10-28 | Wed | Phase 1: Foundations and critical fixes | S2 14:00-16:30 | RLS runtime role | DB | C04 | Create app role NOBYPASSRLS; migrations use owner; update config and docs | Tests pass with runtime role; RLS enforced | Not started
2 | 2026-10-28 | Wed | Phase 1: Foundations and critical fixes | S3 17:00-18:30 | CI: Android assemble + Playwright | CI/CD | E01 | Add Android job (JDK 17, Gradle cache) and Playwright job against local stack | All four CI jobs green | Not started
3 | 2026-10-29 | Thu | Phase 1: Foundations and critical fixes | S1 09:30-12:00 | Security headers and CSP | Web | C08, C09, E15 | Enable CSP with nonces; allow microphone on /glasses; verify voice | CSP on; glasses voice works in Chrome | Not started
3 | 2026-10-29 | Thu | Phase 1: Foundations and critical fixes | S2 14:00-16:30 | Proxy trust and shared rate limits | API | C10, C11 | Set trusted hop count; move rate-limit store to Redis/Postgres | Limits hold across instances (test) | Not started
4 | 2026-10-30 | Fri | Phase 1: Foundations and critical fixes | S1 09:30-12:00 | Glasses bridge hardening | Android bridge | C06 | Allow-list Hydris origin, block navigation, grant only camera/mic for our origin | Foreign page gets no bridge; manual test | Not started
4 | 2026-10-30 | Fri | Phase 1: Foundations and critical fixes | S2 14:00-16:30 | Android release signing | Android | C05, E09 | Release keystore from env/CI secret; R8 on; signed AAB in CI artifact | Signed release AAB builds in CI | Not started
4 | 2026-10-30 | Fri | Phase 1: Foundations and critical fixes | S3 17:00-18:30 | Dependency and secret scanning | Security | E15 | Dependabot/renovate, npm audit gate, gitleaks in CI | Scans run; no high findings open | Not started
5 | 2026-10-31 | Sat | Phase 1: Foundations and critical fixes | S1 09:30-12:00 | Device token storage (glasses web) | Glasses web | C12 | Move refresh token to httpOnly cookie flow or encrypted IndexedDB; short access tokens | No tokens in localStorage | Not started
5 | 2026-10-31 | Sat | Phase 1: Foundations and critical fixes | S2 14:00-16:30 | Android correctness fixes | Android | C21, C22, C26 | Render actions from allowedActions; fix Sensors nav; mutex on device refresh | Manual test on emulator; no regressions | Not started
6 | 2026-11-01 | Sun | Phase 1: Foundations and critical fixes | S1 09:30-12:00 | Week 1 regression and demo check | QA | - | Full demo walk-through (web, console, glasses, Android); fix blockers | Demo works end to end | Not started
6 | 2026-11-01 | Sun | Phase 1: Foundations and critical fixes | S2 14:00-16:30 | Docs sync | Docs | C33, C34 | Update PRD Resolve, pairing TTL, cron cadence, docdetect comment | Docs match code | Not started
7 | 2026-11-02 | Mon | Phase 1: Foundations and critical fixes | S1 09:30-12:00 | Buffer / catch-up | All | - | Close any open Phase 1 items | Phase 1 exit: CI green, P0 security fixes merged | Not started
7 | 2026-11-02 | Mon | Phase 1: Foundations and critical fixes | S2 14:00-16:30 | Weekly retro and plan week 2 | All | - | Retro; update statuses in this sheet | Week 2 owners confirmed | Not started
8 | 2026-11-03 | Tue | Phase 2: Backend hardening and data | S1 09:30-12:00 | Reliable background jobs | Jobs | C13, E05 | Per-minute scheduler; idempotent job runner with locking; job run log | Stale-data alarm fires within 2 min (test) | Not started
8 | 2026-11-03 | Tue | Phase 2: Backend hardening and data | S2 14:00-16:30 | Health and readiness | Ops | C14 | DB ping, migration version, build SHA in /api/health | Health fails when DB down | Not started
8 | 2026-11-03 | Tue | Phase 2: Backend hardening and data | S3 17:00-18:30 | Migrations in deploy step | Deploy | C31 | Run drizzle migrate in CI before promote; remove cold-start migrate | Cold start without migration | Not started
9 | 2026-11-04 | Wed | Phase 2: Backend hardening and data | S1 09:30-12:00 | Email provider | Email | C16, E03 | Resend/SES adapter behind mail interface; send outbox; sent_at; templates | Invite and reset emails arrive | Not started
9 | 2026-11-04 | Wed | Phase 2: Backend hardening and data | S2 14:00-16:30 | Outbox purge and link expiry | Email | C16, C18 | Purge sent mail after 7 days; expire tokens | Purge job tested | Not started
10 | 2026-11-05 | Thu | Phase 2: Backend hardening and data | S1 09:30-12:00 | Object storage for audit images | Storage | C17, E04 | Blob/S3 adapter; write new pages to storage; signed URLs; PDF reads from storage | New scans store no base64 in DB | Not started
10 | 2026-11-05 | Thu | Phase 2: Backend hardening and data | S2 14:00-16:30 | Backfill migration | Storage | C17 | Script moving existing base64 pages to storage; verify counts | All pages migrated; DB size drops | Not started
10 | 2026-11-05 | Thu | Phase 2: Backend hardening and data | S3 17:00-18:30 | Attachments to storage | Storage | E04 | Same adapter for attachments | Downloads served by signed URL | Not started
11 | 2026-11-06 | Fri | Phase 2: Backend hardening and data | S1 09:30-12:00 | Observability: errors | Observability | E02 | Sentry for API, web and Android; release tags; PII scrubbing | Errors visible with stack traces | Not started
11 | 2026-11-06 | Fri | Phase 2: Backend hardening and data | S2 14:00-16:30 | Observability: logs and uptime | Observability | E02 | Structured request logs with tenant/request IDs; uptime monitor; alert routes | Alert reaches on-call channel | Not started
12 | 2026-11-07 | Sat | Phase 2: Backend hardening and data | S1 09:30-12:00 | Data integrity migration | DB | C29 | Add missing FKs, GIN index for search, resolve processing status | Migration applied; tests pass | Not started
12 | 2026-11-07 | Sat | Phase 2: Backend hardening and data | S2 14:00-16:30 | Retention schedule | Data | C18 | Retention per table (telemetry, events, mail, audit pages) as config + purge jobs | Purge jobs run in staging | Not started
12 | 2026-11-07 | Sat | Phase 2: Backend hardening and data | S3 17:00-18:30 | Roles decision | Product | C30 | Decide auditor access to audit log; update roles.ts and tests | Decision recorded | Not started
13 | 2026-11-08 | Sun | Phase 2: Backend hardening and data | S1 09:30-12:00 | OpenAPI generation | Contracts | C32, E13 | Generate OpenAPI from zod route schemas; publish /api/openapi.json | Spec covers all routes | Not started
13 | 2026-11-08 | Sun | Phase 2: Backend hardening and data | S2 14:00-16:30 | Typed clients | Contracts | E13 | Generate TS client for web and Kotlin models for Android; replace hand models gradually | Android compiles with generated models | Not started
14 | 2026-11-09 | Mon | Phase 2: Backend hardening and data | S1 09:30-12:00 | Staging environment | Deploy | - | Staging project + DB branch; seed; env matrix documented | Staging URL live | Not started
14 | 2026-11-09 | Mon | Phase 2: Backend hardening and data | S2 14:00-16:30 | Week 2 retro | All | - | Update sheet; plan week 3 | Phase 2 exit: jobs, email, storage, observability live | Not started
15 | 2026-11-10 | Tue | Phase 3: Mobile and frontend production quality | S1 09:30-12:00 | Android MFA | Android | C28, E07 | TOTP step after password; error states; tests | MFA user signs in on phone | Not started
15 | 2026-11-10 | Tue | Phase 3: Mobile and frontend production quality | S2 14:00-16:30 | Android inspections: data layer | Android | E06 | Room entities for rounds/steps; repository; op IDs for idempotent replay | Unit tests for outbox | Not started
16 | 2026-11-11 | Wed | Phase 3: Mobile and frontend production quality | S1 09:30-12:00 | Android inspections: screens | Android | E06 | Round list, step-by-step entry, checklist, notes, submit | Round completed on emulator | Not started
16 | 2026-11-11 | Wed | Phase 3: Mobile and frontend production quality | S2 14:00-16:30 | Offline replay | Android | E06 | WorkManager sync, conflict handling, offline banner | Airplane-mode round syncs later | Not started
16 | 2026-11-11 | Wed | Phase 3: Mobile and frontend production quality | S3 17:00-18:30 | Photo steps | Android / glasses | E16 | Capture with glasses or phone camera into step attachments | Photo step saved | Not started
17 | 2026-11-12 | Thu | Phase 3: Mobile and frontend production quality | S1 09:30-12:00 | Android tests | Android | E08 | JUnit for DocDetect, OCR row pairing, repository; Compose UI tests for login/home | Tests in CI | Not started
17 | 2026-11-12 | Thu | Phase 3: Mobile and frontend production quality | S2 14:00-16:30 | DAT fixes | Android | C23, C24, C25, C27 | Stop DAT stream; site picker; shared hardware ID; Gradle repo for DAT | Clean build from fresh clone | Not started
18 | 2026-11-13 | Fri | Phase 3: Mobile and frontend production quality | S1 09:30-12:00 | Design tokens single source | Design | C20, E17 | Tokens JSON -> CSS vars, HUD constants, Kotlin Hx | One severity palette everywhere | Not started
18 | 2026-11-13 | Fri | Phase 3: Mobile and frontend production quality | S2 14:00-16:30 | Contrast and accessibility | Design | C19, E24 | Fix HUD and chip contrast; chart descriptions; text scale | All pairs 4.5:1 or better | Not started
18 | 2026-11-13 | Fri | Phase 3: Mobile and frontend production quality | S3 17:00-18:30 | Mobile hardening | Android | E23 | Certificate pinning, Play Integrity, backup rules | Pinning verified | Not started
19 | 2026-11-14 | Sat | Phase 3: Mobile and frontend production quality | S1 09:30-12:00 | Console polish | Web | - | Empty/loading/error states audit; pagination on long lists; keyboard access | Console UX checklist passes | Not started
19 | 2026-11-14 | Sat | Phase 3: Mobile and frontend production quality | S2 14:00-16:30 | Glasses web polish | Glasses web | - | Overlap check at all viewports; offline queue indicator; voice error states | No overlaps; checks scripted | Not started
20 | 2026-11-15 | Sun | Phase 3: Mobile and frontend production quality | S1 09:30-12:00 | Play internal testing | Android | E09 | Play Console app, internal track, privacy policy, data safety form | Testers install from Play | Not started
20 | 2026-11-15 | Sun | Phase 3: Mobile and frontend production quality | S2 14:00-16:30 | Week 3 regression | QA | - | Full regression on staging with Android build | No P0/P1 bugs open | Not started
21 | 2026-11-16 | Mon | Phase 3: Mobile and frontend production quality | S1 09:30-12:00 | Buffer / catch-up | All | - | Close Phase 3 items | Phase 3 exit: Android pilot-ready build | Not started
21 | 2026-11-16 | Mon | Phase 3: Mobile and frontend production quality | S2 14:00-16:30 | Week 3 retro | All | - | Update sheet; hardware booked for week 4 | Glasses and test phones ready | Not started
22 | 2026-11-17 | Tue | Phase 4: Hardware validation, AI quality, pilot readiness | S1 09:30-12:00 | Ray-Ban Meta setup | Glasses | E10 | Meta AI app, Developer Mode, register Hydris Field; GLS-T01 to T05 | Registration and permissions pass | Not started
22 | 2026-11-17 | Tue | Phase 4: Hardware validation, AI quality, pilot readiness | S2 14:00-16:30 | Camera and capture button | Glasses | E10 | GLS-T06 to T10: stream, photo, capture button, guided A4 scan | Scan from glasses reaches console | Not started
22 | 2026-11-17 | Tue | Phase 4: Hardware validation, AI quality, pilot readiness | S3 17:00-18:30 | Speech and voice | Glasses | E10, E12 | GLS-T11 to T15: glasses mic, wake word, TTS through glasses | Hey Hydris works on glasses | Not started
23 | 2026-11-18 | Wed | Phase 4: Hardware validation, AI quality, pilot readiness | S1 09:30-12:00 | OCR benchmark set | AI / OCR | E11 | Build 120-page ground truth; script field/decimal/table accuracy | Baseline accuracy report | Not started
23 | 2026-11-18 | Wed | Phase 4: Hardware validation, AI quality, pilot readiness | S2 14:00-16:30 | OCR improvements | AI / OCR | E11 | Tune thresholds, plausibility rules from benchmark failures | Silent error rate at target | Not started
24 | 2026-11-19 | Thu | Phase 4: Hardware validation, AI quality, pilot readiness | S1 09:30-12:00 | Voice test set | AI / Voice | E12 | 600 utterances incl. Indian English accents; false accept/reject | Voice report vs targets | Not started
24 | 2026-11-19 | Thu | Phase 4: Hardware validation, AI quality, pilot readiness | S2 14:00-16:30 | Assistant grounding checks | AI | - | Zero answers with numbers not from tools; data age stated | Automated check in CI | Not started
25 | 2026-11-20 | Fri | Phase 4: Hardware validation, AI quality, pilot readiness | S1 09:30-12:00 | Load and performance tests | Performance | E14 | k6: ingest, SSE fan-out, dashboard; fix slow queries | Capacity documented; p95 targets met | Not started
25 | 2026-11-20 | Fri | Phase 4: Hardware validation, AI quality, pilot readiness | S2 14:00-16:30 | Backup and restore drill | Ops | E18 | Point-in-time restore to a branch; runbook timing | Restore within RTO target | Not started
26 | 2026-11-21 | Sat | Phase 4: Hardware validation, AI quality, pilot readiness | S1 09:30-12:00 | Security review | Security | E15 | Pen-test checklist (OWASP ASVS L2), fix findings, threat model update | No high findings open | Not started
26 | 2026-11-21 | Sat | Phase 4: Hardware validation, AI quality, pilot readiness | S2 14:00-16:30 | Privacy and compliance pack | Compliance | - | DPDP notice, retention, DPA, subprocessors list (Vercel, Neon, Anthropic) | Pack ready for customer review | Not started
27 | 2026-11-22 | Sun | Phase 4: Hardware validation, AI quality, pilot readiness | S1 09:30-12:00 | Pilot onboarding dry run | Ops | - | Create pilot org, sites, sensors, users, profiles, pair glasses (runbook) | Onboarding under 1 day | Not started
27 | 2026-11-22 | Sun | Phase 4: Hardware validation, AI quality, pilot readiness | S2 14:00-16:30 | Training material | Ops | - | Operator and admin quick guides, 5-minute videos | Materials reviewed | Not started
28 | 2026-11-23 | Mon | Phase 4: Hardware validation, AI quality, pilot readiness | S1 09:30-12:00 | Buffer / catch-up | All | - | Close Phase 4 items | All P0 items done | Not started
28 | 2026-11-23 | Mon | Phase 4: Hardware validation, AI quality, pilot readiness | S2 14:00-16:30 | Week 4 retro | All | - | Update sheet; go/no-go checklist draft | Checklist ready | Not started
29 | 2026-11-24 | Tue | Phase 5: Release | S1 09:30-12:00 | Release candidate | Release | - | Freeze; tag RC; deploy to staging; full regression | RC signed off by QA | Not started
29 | 2026-11-24 | Tue | Phase 5: Release | S2 14:00-16:30 | Production deploy | Release | - | Promote to production; migrations; smoke tests; monitoring watch | Production healthy for 24 h | Not started
29 | 2026-11-24 | Tue | Phase 5: Release | S3 17:00-18:30 | Go/no-go review | Product | - | Review exit criteria (QA plan); decide pilot start | Decision recorded | Not started
30 | 2026-11-25 | Wed | Phase 5: Release | S1 09:30-12:00 | Hypercare | Ops | - | Monitor errors, alarms latency, scan verification turnaround; fix fast | No Sev1/Sev2 open | Not started
30 | 2026-11-25 | Wed | Phase 5: Release | S2 14:00-16:30 | Month retrospective and next roadmap | All | E19 to E22 | Plan e-signature, localisation, edge gateway, compliance reports | Next-month plan agreed | Not started